## Tasks
Date Created | Date Completed | Category | Name | Comments | Notes
2022-10-30 |  | Admin | architecture | Develop web-based portal page that requires credentails that will enable self service of tests
2022-10-30 | 2022-11-03 | Admin | push | Add option to update Grafana
2022-10-30 |  | Admin | push | Add options to seeds for check¦delete
2022-10-30 | 2022-11-03 | Admin | push | Add option to check amount of storage in tld, comp, and portal/images
2022-10-31 |  | Akamai | property | Update property to include all best practices | - caching - DNS - Enable mPulse SPA monitoring for Grafana
2022-10-30 |  | Github | readme | Update Readme.md to include TOC, Installation, and setting up tests
2022-10-30 |  | Grafana | admin | Modify system admin dashboard to start tracking core files on each server. Create new panel that coorelates errors and core files in same graph
2022-11-03 |  | Grafana | alerting | Generate alerts and send output to Knuckles | http://170.187.161.192/api/namespaces/demo/tree/sitespeed-test-done?op=execute { the body should be any json I think is useful - offending metric - tested url - tested device - connectivity speed - latency - region }
2022-10-30 |  | Grafana | dashboard | Modify Google dashboard to repeat all panels for CrUX data in the pie chart panel | - Rename variable display name Function to Percentiles on all dashboards - Break up Page Metrics into Performance Metrics and Browsr Metrics - Break Google into Lighthouse and CrUX - Break Leaderborad into Performance Leaderboard and Browser Leaderboard - Implement repeat panels on CrUX to correctly display pie charts for every domain and page
2022-11-03 |  | Grafana | dashboard | Open a Github issue to get coloring added to table capability
2022-11-03 |  | Grafana | logging | Implement Loki instance and then enable User Insights
2022-10-30 |  | Portal | admin | Create diagram of existing architecture that includes all servers and associated firewall rules
2022-10-30 |  | Portal | admin | Update sitespeed.pptx
2022-10-30 |  | Sitespeed | admin | Evaulate storing test HTML results on Linode in order to free up local storage
2022-11-03 | 2022-11-08 | Sitespeed | config | Reduce the number of percentiles collected. Evaluate data collecte din Graphite to see what makes sense | - Take a look at actual .wsp files to see how many runs are required to populate a unique value - Modify config.json collection - Modify functions variable
2022-11-04 |  | Sitespeed | config | Evaluate the possibility of collecting and storing LCP subcomponents
2022-10-30 |  | Sitespeed | core | Alter master.sh and google.sh to check for core* in all folders after each run and log them in sitespeed_log namespace on graphite
2022-10-30 | 2022-11-09 | Sitespeed | docker | Evaluate the necessity of running docker system prune on all servers on a regular basis
2022-10-30 |  | Sitespeed | feature | Evaluate using pulling WPT using my API key
2022-11-04 | 2022-11-09 | Sitespeed | master | Reduce the number of days for saving annotations to 7. Modify master.sh and setting in delete sql events on graphite
2022-11-03 |  | Sitespeed | portal | Add LCP and other key metrics to main portal screen in lower left hand corner
2022-10-30 |  | Sitespeed | push | Add option to check and delete core files on each server/ Be sure to only delete core fiels that actually exist
2022-11-04 |  | Sitespeed | metrics | Determine if largest assets are stored in Graphite

## Host Names
Host | Akamai Edge Hostname | Origin Name | Origin IP
sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | portal.sitespeed.akadns.net | 66.175.214.170
grafana.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | grafana.sitespeed.akadns.net | 198.74.57.70
us-east.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | us-east.sitespeed.akadns.net | 96.126.106.115
us-central.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | us-central.sitespeed.akadns.net | 45.79.46.26
us-west.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | us-west.sitespeed.akadns.net | 173.230.148.187
toronto.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | toronto.sitespeed.akadns.net | 192.46.223.151
london.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | london.sitespeed.akadns.net | 213.219.37.194
frankfurt.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | frankfurt.sitespeed.akadns.net | 139.162.179.224
mumbai.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | mumbai.sitespeed.akadns.net | 172.105.41.246
tokyo.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | tokyo.sitespeed.akadns.net | 172.104.77.85
singapore.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | singapore.sitespeed.akadns.net | 139.162.35.83
sydney.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | sydney.sitespeed.akadns.net | 194.195.123.137
psi-crux.sitespeed.akamai.com | sitespeed.akamai.com.edgesuite.net | psi-crux.sitespeed.akadns.net | 172.104.9.87

## mPulse
Tenant | EPIC
Tenant ID | 252429
Domain | Sitespeed
Domain ID | 245842
API Key | LHUYN-24HDW-NSJ3K-BA96G-WCMHG